## Sheet1
Implement tiles			done
Tile heights and ramps			done
pathfinding			done
Game loop			done
	add game over		done
	fix off-by-one in turn counter		done
Implement basic programs			done
implement camera control			done
implement game manager			done
create Program UI			done
	highlight selected/targeted programs on board		done
	adjust alpha of stealthed programs		done
	show player proposed movement paths		done
		fix cleanup on movement paths	done
	visualize AI sight range		done
	implement Hacking status panel		done
	visual feedback for hacked objects		done
Implement control scheme			done
Enemy Programs			done
Implement basic player Program types			done
Implement basic enemy program types			done
Implement AI behaviours			done
Create tutorial dungeon			done
	Do tutorial text promts		done
Implement Proc-gen dungeons			done
	generate rooms		done
	generate enemies		done
	generate security nodes		done
	generate obstacles		done
	generate collectibles		done
Implement Firewalls			done
Create collectibles			done
Implement Vaults			done	-these are just firewalls on collectables
Implement Terminals			done
Create tutorial			done
Implement Program keywords			done
	ghost		done
	sensor		done
	flying		done
	hit and run		done
	recover		done
	armored		done
Implement ports			done
Implement security hub			done
Create inter-mission scenes			in progress
	menu		done
	desktop		done
	newsfeed		TODO
	credits		done
	shop		done
	reference		TODO
Implement player progression			done
	enemy assignment		done
	alpha enemy types		done
Juice for Alpha release			done
	attack/hack animations		done
	explore animation		done
	sound effects		done
	bg music		done
	clean up UI layout		done
Alpha Polish			done
	fix camera config		done
	add logic to level generator to avoid overlapping rooms		done
	Implement terminal cameras		done
				Alpha release
Implement scanners			done
Implement upgrades			done
design corps			in progress
	create names		done
	mechanical identites		in progress
		-dungeon layout	in progress
		-enemy suite	in progress
		-unique features	in progress
	bad practices		TODO
design more player programs			in progress
design more enemy programs			in progress
design more rooms			in progress
Online presence			in progress
	itch page		in progress
		-screenshots	in progress
		-gameplay footage	in progress
		-discussion topics, introductions and CTA	TODO
		-try webgl build	TODO
	social media		TODO
		-plug the itch page	TODO
		-identify influencers	TODO
Get cover art			TODO
death animations/ particle effects			done
soft endpoint			TODO
Incorporate user suggestions			TODO

			TODO	Beta Release
unit models/sprites			TODO
Dungeon backgrounds			TODO
Sound design			TODO
Game writing			TODO
Production Release			TODO