## Sheet1
Implement tiles			done
Tile heights and ramps			done
pathfinding			done
Game loop			in progress
Implement basic programs			done
implement camera control			done
implement game manager			done
create Program UI			done
	highlight selected/targeted programs on board		done
	adjust alpha of stealthed programs		done
	show player proposed movement paths		done
	visualize AI sight range		done
Implement control scheme			done
Enemy Programs			done
Implement basic player Program types			done
Implement basic enemy program types			done
Implement AI behaviours			done
Create tutorial dungeon			in progress
Implement Proc-gen dungeons			in progress
	generate rooms, randomize height		done
	add ramps for access		done
	generate enemies		TODO
	generate security nodes		TODO
	generate obstacles		TODO
	generate collectibles		TODO
Implement Firewalls			in progress
Create collectibles			TODO
Implement Vaults			TODO
Implement Terminals			in progress
Create tutorial			in progress
Implement Program keywords			in progress
Implement ports			in progress
Implement security hub			TODO	Alpha Release
Implement scanners			TODO
Implement upgrades			TODO
design corps			TODO
Implement player progression			TODO	Beta Release
unit models/sprites			TODO
Action animations			TODO
Dungeon backgrounds			TODO
Sound design			TODO
Game writing			TODO
Production Release			TODO