## Sheet1
Implement tiles			done
Tile heights and ramps			done
pathfinding			done
Game loop			in progress
	add game over		done
	fix off-by-one in turn counter		TODO
Implement basic programs			done
implement camera control			done
implement game manager			done
create Program UI			done
	highlight selected/targeted programs on board		done
	adjust alpha of stealthed programs		done
	show player proposed movement paths		done
		fix cleanup on movement paths	done
	visualize AI sight range		done
	implement Hacking status panel		done
	visual feedback for hacked objects		done
Implement control scheme			done
Enemy Programs			done
Implement basic player Program types			done
Implement basic enemy program types			done
Implement AI behaviours			done
Create tutorial dungeon			in progress
	Do tutorial text promts		TODO
Implement Proc-gen dungeons			in progress
	generate rooms		done
	generate enemies		done
	generate security nodes		done
	generate obstacles		done
	generate collectibles		done
Implement Firewalls			done
Create collectibles			done
Implement Vaults			done	-these are just firewalls on collectables
Implement Terminals			done
Create tutorial			in progress
Implement Program keywords			in progress
	ghost		done
	sensor		to test
	flying		done
	hit and run		done
	recover		done
	armored		to test
Implement ports			done
Implement security hub			done
Create inter-mission scenes			in progress
	menu		done
	desktop		done
	newsfeed		TODO
	credits		TODO
	shop		done
	customize		TODO
Implement player progression			in progress
	enemy assignment		done
	alpha enemy types		in progress
Juice for Alpha release			TODO
	attack/hack animations		TODO
	explore animation		in progress
	sound effects		TODO
	bg music		TODO
	clean up UI layout		TODO
Alpha Polish			TODO
	fix camera config		done
	add logic to level generator to avoid overlapping rooms		done
	Implement terminal cameras		TODO
				Alpha release
Implement scanners			TODO
Implement upgrades			TODO
design corps			TODO
				Beta Release
unit models/sprites			TODO
	contact Wendy thru Michael		TODO
Dungeon backgrounds			TODO
Sound design			TODO
	contact Nina Richards		TODO
Game writing			TODO
Production Release			TODO